## Sheet1
PO | Title | Supplier | Rev | Job # | OE Date | PO Effective Date | PO Delivery Date | FAT | Witness | Manufacturing Completed date | SUBMISSION OF DOCS | Predicted Date |  | Note | % completed (Manufacturing) | % completed (Doc) | Forcast | Expeditor | Milestones
RT79-87920-PN-R005 | CTI BORE GAUGE TOOL FOR C1R | RTD | 0 | J# 71669 | 2024-12-03 | 2024-11-29 | 2025-03-26 | ✓ |  | Jan-23-26 | Feb-5-26 | Feb-13-26 | Jan-22-26- MTR, -still waiting for approval Jn-22-26- Once Mfg is completd- Witness Notiifiction wiill be sent, |  | 95% | 75% | changed | David Weldon | Milestone # 1- 35% of Unprice PO for Mat'l : Inv# 52477 # 2- 30% Function /accept test : Inv# 52877 # 3- 35 % upon Comp & Delv Inv# All procedures received - Approved
RT98-87920-PN-R006 | CTI BORE GAUGE TOOL FOR QINSHAN - | 0 | 0 | J# 71742 | 2024-12-03 | 2025-01-07 | 2025-01-25 | ✓ |  | 2025-11-06 | 2025-11-26 | Jan 23, 26 Jan 16, 26 | \Nov-5-25- Trigger Lock's manufacturing was completed-currently reassembly, prepare QA Docs Nov-6-25- Manufacturing completed-waiting for preparing trigger part's DIR, waiting approval for other Docs Nov-26-25- CfC, DIR, FAT submitted-waiting for approval Dec-11-25-Under correction of DIR Dec-17-25-DDR submitted-waiting for approval Jan-5-26- DDR9002 resubmitted-waiting for approval Jan-7-26- CfC, DIR are not accepted-need to correct and resubmit Jan-14-26- MTR, CfC, DIR-still waiting for approval |  | 95% | 90% | changed | David Weldon | Milestone # 1- 35% of Unprice PO for Mat'l : Inv# 52478 # 2- 30% Function /accept test : Inv# 52876 # 3- 35 % upon Comp & Delv Inv#
RT98-88010-PN-R009 | GROUP 7G TOOLS FOR QINSHAN | RTD |  | J# 72580~ 72583 | 7/22/25 | 7/22/25 | Sept-29-25 | ✓ |  | 2025-11-17 | 2025-12-01 | Jan 23, 26 Jan 16, 26 | OCT-22-25- RT-87000-70201-6100-1-GA-B-has an issue with the final shape. Since the manufacturing complete date will be determined once the countermeasure is decided, a tentative schedule is provided for now. Oct-29-25- Accept issue about RT-87000-70201-6100-1-GA-B, preparing QA Docs Nov-5-25- J#72580 need to rework-There was a comment that rework is required for the approved DDR. Nov-12-25- The date needs to be changed. The rework requires a large machine-since processing other high-priority parts, the adjustment has taken longer than expected. Dec-9-25- Submitted FAT report-still pending Jan-6-26- MTR and DIR were resubmitted-waiting for approval Jan-14-26- MTR was accepted, DIR still waiting for approval |  | 95% | 40% | On Schedule | Etianne Machado | NO Milestones
RT98-88010-PN-R008- Rev.1 | GROUP 7F OF TOOLS | RTD |  | J# 72589-72599 J# 73000 | 7/22/25 | 7/22/25 | Sept-25-25 | ✓ |  | Dec 9, 25 Nov 28, 25 | Dec 23, 25 Dec 16, 25 | Jan 23, 26 Jan 13, 26 | Oct-22-25- Since currently waiting for the inspection of the detail parts also assembly has not been completed, it is necessary to reschedule the shipping date. Oct-29-25- Due to delays in the inspection and assembly processes-need to change the date. Nov-12-25- Ship date need to be changed-waiting for Heat Treat and painting Nov-26-25- Ship date need to be changed-Because ‘RT-88000-70034-000-1-GA-E’ is taking longer than planned. Dec-10-25- Manufacturing completed, preparing QA Docs Dec-17-25- MTR, C of C will submit in Dec-18, preparing FAT report Jan-7-26- MTR, CfC, DIR were accepted, FAT report need to resubmit Jan-8-26- submitted revised FAT report-still waiting for approval |  | 95% | 40% | On Schedule | Etianne Machado | NO MILESTONES
RT79-87900-PN-R003 | C6-BORE GAUGE AND C6-BORE GAUGE-NARROW LANDING FOR C1R | RTD | 0 | J# 71852-71853 | 2024-12-30 | 2024-12-24 | 2025-07-31 | ✓ | 2026-01-28 | Jan 23, 26 tentitive Dec 23, 25 | Jan 30, 26 tentitive Jan 6, 26 | Feb 13, 26 Jan 16. 26 | Oct-29-25- Tip part's dwg issue- need to get new design dwg, remake tips Nov-5-25- Remakining Tip parts- reassembly Nov-7-25- sent e-mail for assembly issue, DDR9003 submitted-waiting for approval Nov-12-25- Tip part : waiting for Candu answer, assembly issue Nov-25-25- received custom probe tips dwg-need to submit quote Dec-1-25- new tips doesn't work so Steve will tell to Candu Dec-3-25- Candu Inspector came to check the issue, RTD need to send new desighin-there are not only tip issue.-redesign issue pending Jan-7-26- Need to submit DDR for rework (Probe Tips and the Peek cone) Jan-14-26- Tip parts machining done (for RT79), in inspection |  | 80% | 75% | ON SCHEDULE | Laila Parveen | Milestone 1- 30% of Unpriced PO Inv# 52795 2- 70% competion / Delv Inv# Feb-26-25- All procedures received approved
RT98-87900-PN-R003 | C6-BORE GAUGE AND C6-BORE GAUGE-NARROW LANDING FOR C1R | RTD |  | J# 72622-72623 | Aug-1-25 | Aug-1-25 | Nov-28-25 | ✓ | 2026-02-18 | Feb 13, 26 tentitive Nov 26, 25 | Feb 20, 26 tentitive Dec 3, 25 | Mar 6, 26 Jan 16, 26 | Oct-29-25- Since the sighed PO with a shipment date of Dec28 has been submitted and approved, the shipment date will be changed to Dec 28. Nov-25-25- received custom probe tips dwg-need to submit quote Dec-1-25- new tips doesn't work so Steve will tell to Candu Dec-3-25- Candu Inspector came to check the issue, RTD need to send new desighin-there are not only tip issue.-redesign issue pending Jan-7-26- Need to submit DDR for rework (Probe Tips and the Peek cone) Jan-14-26- Due to an insufficiency in the chrome process, the chrome process needs to be carried out again, so the schedule has been changed. |  | 70% | 15% |  | AMritha Gopan | Milestone 1) 30%- Upon Submission Unpriced PO 2) 70% Upn Delivery of all equipment & Docs
RT79-87630-PN-R005 | VRS MANUAL RETRIEVAL TOOL | RTD | 0 | j# 72395 | 2025-05-01 | May-20-25 | Aug-27-25 | N/A |  | pending Jan 9, 26 Nov 24, 25 | pending Jan 16, 26 Dec 1, 25 | Jan 30, 26 Dec 17, 25 | Oct-22-25- Quote will be submitted in Oct-22. Still waiting for Instection, need to Assembly-The delivery date need to be changed. Nov-5-25- Waiting approval for DDR9005,Reference quote#LP72395 Nov-12-25- Change the manufacturing date-to complete order glue Dec-11-25- We obtained the cloth part information from Candu, so purchasing is required-we will receive the cloth in this week-need to machine Dec-17-25- Need to change the date-due to Due the manufacturing progress being behind schedule. Jan-7-26- Still working on manufacturing Jan-14-26- waiting answer for the manufacturing progress and the schedule from shopping floor. |  | 75% | 80% | On Schedule | Laila Parveen | Milestone: 1) 30% upon submittal of Unpriced PO 05/27/25 INV# 52865 2) 70% Upon Delivery of Deliverable & Documents 8/27/25 INV#
RT98-87540-PN-R001 | POSITIONING ASSEMBLY (PA) HARDWARE REMOVAL TOOL FOR QINSHAN | RTD | 0 | j# 71829 | 2024-12-23 | 2024-12-19 | 2025-05-02 | ✓ |  | 2025-12-05 | 2025-12-12 | Jan 23, 26 Jan 16, 26 | Oct-22-25- (Docs) DIR-Waiting for Candu approval Oct-29-25- The casters and floor lock need to be reassembled with new ones. The specifications have already been shared with the Candu side. Oct-31-25- DIR was resubmitted Nov-5-25- Still waiting for Caster confirmation. Nov-12-25- Doc package resubmitted-waiting fo rapproval Nov-26-25- Waiting for the answer about caster and lock. Dec-9-25- The quote for the caster and lock has been submitted-waiting for Candu answer-pending Jan-6-26- waiting for Candu answer for the quote-pending (email Jan-6 11:54) Jan-14-26- waiting for Candu answer for the quote-pending (email Jan-6 11:54) |  | 90% | 90% | ON SCHEDULE | David Weldon | Milestone: #1- 30% receipt of Major Material: Inv# 52544 #2- 30% Upon 75% completion : Inv# 52816 #3- 40% completion/ delv : Inv #
RT98-87290-PN-R004 | MATERIAL HANDLING CART | RTD |  | J# 72643 | Aug-12-25 | Aug-12-25 | Dec-17-25 | ✓ | 2026-01-07 | Jan 9, 26 Dec 2, 25 | tentitive Dec 9, 25 | Jan 23, 26 Jan 9, 26 | Oct-29-25- Ready to Loadtest-MPI, paint,reassembly Nov-25-25- For some of the carts, the stainless steel cover (RT-87920-7006-1-DD-D) is slightly bowed/bumped up in the middle. Dec-11-25- Checking what kind of test we need (FAT) Dec-17-25- Finished FAT-need to witness, confirming Doc submission date Jan-7-26- After completing the FAT witness, Candu : to confirm the weight of the carts (extra 300 pounds)-accepted RTD : to complete some welding area (3pc)-completed for manufacturing (Jan-9) Jan-14-26- Waiting FTP link from Candu (email Jan-13 9:12 AM) |  | 95% | 40% |  | Amritha Gopan | Milestones:
RT79-87630-PN-R011 | VRS PT LUNCHBOX FOR C1R | RTD |  | J#72645-72647 | Aug-14-25 | Aug-14-25 | Dec-11-25 | ✓ | 2026-02-25 | Feb 20, 26 Jan 30, 26 | Feb 27, 26 Feb 6, 26 | Mar 13, 26 Feb 20, 26 | Nov-12-25- The shipping date needs to be changed. Since “B-12995-1622-0011” was scrapped, we need to order new material, but the lead time is 3 weeks. All dates are tentative, as they depend on the timing of material arrivals. Nov-26-25- The shipping date needs to be changed-Since ‘B-12995-1622-0011’ was scrapped and the lead time (3 weeks) to procure the material was long as well. Dec-10-25- We need to send subcontrackt but the company shutdown 2W so we need to pushout date. Jan-7-26- Still working on manufacturing Jan-14-26- Need to change the date goe to the dimensions of the area for the EDM process are large, so it takes longer time than expected. |  | 65% | 10% |  | Laila Parveen | 1) 20% Upon submission of Procedures Inv# 2) 20% Upon Submission of Unpriced PO Inv# 3) 60% upon delivery & Doc Inv# KICK OFF MEETING: SEPT-10-25- @ 10 AM
RT79-88030-PN-R001- Rev.1 | GARTER SPRING DETECTION TOOL & SSDO TOOL- | RTD | 0 | J# 72083 ~ 72084 Added J# 72278 | 2025-02-21 | 2025-02-21 | 2025-06-20 | N/A |  | Jan 23, 26 Jan 14, 26 Dec 30, 25 | Jan 30, 26 Jan 21, 26 Jan 6, 26 | Feb 13, 26 Feb 4, 26 Jan 20, 26 | Nov-12-25- Quote submitted-waiting approval (it is take 10-12W to complete rework) Nov-26-25- Since 72084 requires rework, we are checking whether the shipment of the other parts can be moved up. Dec-11-25- waiting for tube reseived-in disassembly,need to reworke-waiting for a response regarding the partial shipment. Dec-17-25- tube received-in reworking-still pending Jan-5-26- Need to change the date due to Inspection backlog-rework was completed(Dec-30), in inspection, need to prepare QA Docs Jan-14-26- Need to change the date due to take longer than planned to complete the inspection. |  | 95% | 60% | NP Processed | David Weldon | MILESTONES: 35%- Submission of unpriced PO for Major Mat'l Inv# 52661 15%- Upon 75% completeion of Mfg Inv# 52993 20%- Ready to perform Functional /Acceptance Test Inv# 10%- Successful completion of Functional/ accept test Inv# 20%- Delivery of Equipment including History File Inv#
RT98-88030-PN-R001- Rev.2 | GARTER SPRING DETECTION TOOL & SSDO TOOL- | RTD | 0 | J# 72085- 72086 Added J# 72279 New Addition J# 72459-72460 | 2025-02-21 | 2025-02-21 | 2025-07-31 | N/A |  | Jan 23, 26 Jan 14, 26 Dec 30, 25 | Jan 30, 26 Jan 21, 26 Jan 6, 26 | Feb 13, 26 Feb 4, 26 Jan 20, 26 | Nov-12-25- Quote submitted-waiting approval (it is take 10-12W to complete rework) Nov-26-25- Since 72084 requires rework, we are checking whether the shipment of the other parts can be moved up. Dec-11-25- waiting for tube reseived-in disassembly,need to reworke-waiting for a response regarding the partial shipment. Dec-17-25- tube received-in reworking-still pending Jan-5-26- Need to change the date due to Inspection backlog-rework was completed(Dec-30), in inspection, need to prepare QA Docs Jan-14-26- Need to change the date due to take longer than planned to complete the inspection. |  | 95% | 60% | NP Processed | DAVID Weldon | FEB-21-2025- This PO processed - Procedures will be submitterd- March-25-25 MILESTONES: 1) 35%- Submis of unpriced PO for Major Mat'l Inv# 52662 2) 15%- Upon 75% completeion of Mfg Inv# 52994 3) 20%- Ready to perform Functional /Acceptance Test Inv# 4) 10%- Successful completion of Functional/ accept test Inv# 5) 20%- Delivery of Equipment including History File Inv#
RT79-88020-PN-R003 | SA TRANSPORT CONTAINER & EF TRANSFER CONTAINER | RTD |  | j# 72605-72606 | 7/25/25 | 7/25/25 | 7/25/25 | N/A |  | Feb 16, 26 Jan 9, 26 | Feb 23, 26 Jan 16, 26 | Mar 9, 26 Jan 30, 26 | Oct-7-28- Receoved 6-pcs of -SA Transport Containers - RTD Needs to Evaluate to confirm delivery dates Nov-5-25- the containers that have been sent findings have been evaluated-Candu will visit to confirm, and will start rework. Nov-26-25- Still on track-waiting for hardware Dec-17-25- Since it takes 3W for the subcontracting process after welding, a change in the schedule is required. Waiting answer from Candu about handle crash and small parts position,"RT-88030-79002-01-GA-D", Identify info. Jan-6-26- Still waiting answer from Candu Jan-14-26- Still waiting for revised dwg from Candu | ` | 25% | 5% | On Schedule | Etianne Machado | Milestones: 1) 25% Upon submission fo Procedures Inv# 2) 25% Upon Receipt of Main Materials Inv# 3) 25% upon Start of Assy Inv# 4) 25% upon delivery of Equipment Inv#
RT79-87840-PN-R002 | CV FME INSPECTION TOOL | RTD | 0 | J# 72517,72906 | june-27-25 | june-27-25 | Nov-17-25 | ✓ |  | Jan 30, 26 Jan 16, 26 | Feb 6, 26 Jan 23, 26 | Feb 20, 26 Feb 6, 26 | Oct-22-25- Due to machining and assembly of the detail parts taking longer than expected, the shipping date has been rescheduled. Oct-29-25- Detail parts machining done-Assembly Nov-5-25- With the addition of the new JOB#72706, all three dates are now tentitive. Nov-12-25- RT-87840-0220-01-GA-2 : 3D model received, still waiting for revised PO Nov-26-25- RT-87840-7000-1000-1-GA-B : Waiting for camera part. Dec-11-25- stll on track-Line#1 : need to check weight,Line#2 : still on track Dec-17-25- stll on track-no issue at this time Jan-6-26- Need to change the date due to Inspection backlog Jan-14-26- Still working on manufacturing |  | J# 72517 80% J#72906 60% | 55% |  | Laila Parveen | Milestones: 1) 30% upon submission of Unpriced PO: Inv# 52867 2) 30% Upon Completion of approx. 50% of project Inv# 3) 15% Upon receipt of Camera, etc. related equop Inv# 4) 25% Upon Delivery of all items & QA Doc Inv#
RT79-88230-PN-R012 | FEEDER TEMPLATES | RTD | 0 | J# 72139-72147 | 2025-03-04 | 2025-03-04 | 2025-10-17 | N/A |  | Feb 13, 26 Jan 23, 26 | Feb 20, 26 Jan 30, 26 | Mar 6, 26 Feb 13, 26 | Oct-29-25- The shipment date has been changed due to a factory's floor capacity issue. Machining done-welding, inspection, assembly Nov-5-25- Stil on track- no issues at this time Nov-12-25- Still on track, no issues at this time. Nov-26-25- The shipping date needs to be changed-the inspection, welding, and assembly are taking longer than originally planned. Dec-11-25- Fit check info should be from Candu Dec-17-25- manufacturing still in progress Jan-7-26- Fit test info-still waiting from Candu, Need to change the date due to Inspection backlog Jan-14-26- Still working on manufacturing |  | 75% | 60% | On Schedule | Laila Parveen | Milestone: 1) 30% upon submittal of Unpriced PO Inv# 52699 2) 15% upon 40% ave.comp of MFG Inv# 52863 3) 15% upon 75% average completion of MFG Inv# 4) 40% Upon Delivery of items and Docs Inv#
RT79-87550-PN-R001- Rev.1 | MANUFACTURE OF SFCR BELLOWS CUT TOOL FOR C1R | RTD | 0 | ( j# 71851 & 71873 - SPARES) J# 72330 ( 2) | 2024-12-30 | 2024-12-24 | 2025-07-04 | ✓ |  | Feb 13, 26 Jan 30, 26 | Feb 20, 26 Feb 6, 26 | Mar 6, 26 Feb 20, 26 | Oct-22-25- Machining is still in progress Oct-29-25- Gear parts (BOM 9) need to modify-EDM made a mistake, scrap so need to make a new piece. Nov-5-25- Stil on track- no issues at this time Nov-12-25- RT-87550-0121-01-GA-E has issue during Inspection- sent e-mail Nov-12 2:23 still waiting for answer Dec-17-25- We need to send some parts to subcontrackt but the company shutdow 2W so we need to pushout date. Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 75% | 65% | ON SCHEDULE | Laila Parveen | Milestone: 1 - 25 % submit Unpriced PO Inv# 52642 2- 15% Receipt oof Major lead it Inv# 52875 3 15% Ready for Assy Inv# 4- 15% -Ready for function/accept. test Inv# 5- 15% successful function test Inv# 6- 15% completeion & delivery Inv#
RT98-87550-PN-R004- Rev.1 | MANUFACTURE OF SFCR BELLOWS CUT TOOL FOR- Qinshan | RTD | 0 | J# 72023- 72024 (Spares) J# 72331 ( 2) | 2025-02-11 | 2025-02-11 | 2025-02-11 | ✓ |  | Feb 13, 26 Jan 30, 26 | Feb 20, 26 Feb 6, 26 | Mar 6, 26 Feb 20, 26 | Oct-22-25- Machining is still in progress Oct-29-25- Gear parts (BOM 9) need to modify-EDM made a mistake, scrap so need to make a new piece. Nov-5-25- Stil on track- no issues at this time Nov-12-25- RT-87550-0121-01-GA-E has issue during Inspection- sent e-mail Nov-12 2:23 still waiting for answer Nov-26-25- Still on track Dec-17-25- We need to send spme parts to subcontrackt but the company shutdow 2W so we need to pushout date. Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 75% | 65% | ON SCHEDULE | Laila Parveen | Feb-15-2025- Order Processed with RT79- Milestone 1 ) 25 % submit Unpriced PO Inv# 52643 2) 15% Receipt oof Major lead it Inv# 52859 3 ) 15% Ready for Assy Inv# 4) 15% -Ready for function/accept. test Inv# 5) 15% successful function test Inv# 6) 15% completeion & delivery Inv#
RT79-87000-PN-R020 | BRT BELLOWS REMOVAL CUTTING TOOL FOR C1R +Electrical | RTD |  | J# 72692-72708 | AUG-29-25 | AUG-29-25 | April-30-26 | ✓ |  | 1set :Mar-26-26 Mar-10-26 Feb-5-26 2set : Apr-30-26 April-9-26 | 1set : Apr-2-26 Mar-17-26 Feb-12-26 2set : May-7-26 April-16-26 | 1set : Apr-16-26 Mar-31-26 Feb-26-26 2set : May-21-26 April-30-26 | Sept-2-25- PO Accept- Signed Back Nov-12-25- on trak- no issues at this time Nov-26-25- Confirming the realistic date for one set Dec-11-25- Still confirming the realistic date for the shipdate Dec-17-25- DDR9001 still pending-need to change the date fo rthe 1st set (still confirming) because of electrical issues (DDR9001) Dec-22-25- We have shared the shipment of 1st set will be delayed, along with the reason for the delay. Jan-6-26- Still working on manufacturing, Confirming Edwin about electrical issues Jan-14-26- Confirmed the realistic date for shipping date |  | 20% | 5% |  | Laila Parveen | Milestones: 1) 30% upon submttal of Unpriced Pos' Inv# 2) 30% upon completion of Purchse of Long Lead and Critical Components & Initation of Mfg activities Inv# 3) 40% Upon Delivery of all items including Documentation
RT79-79112-PN-R002 | SMALL WASTER TRANSFER FLASK | RTD | 0 | J# 72422 | May-26-25 | May-26-25 | Jan-26-26 | ✓ |  | Feb 28, 26 Nov 23, 25 | Mar 6, 26 Nov 30, 25 | Mar 20, 26 Dec 14, 25 | Oct-22-25- Welding is still in progress no issue at this time Oct-29-25- The shipment date has been changed due to a factory's floor capacity issue. Nov-5-25- Confirmed the fablication issue Nov-10-25- FAT Procedure revised Nov-26-25- We cannot change the shipping date due to the shop workload. Dec-17-25- still in machining-still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 45% | 30% | On Schedule | Amritha Gopan | Milestone: 1) 30% upon submittal of Unpriced PO 06/13/25 INV# 52866 2) 30% When Ready for Load Testing 9/15/25 INV# 3) 40% Upon Delivery of all items & Documents1/26/26 INV#
RT98-87530-PN-R001 | GROUP 2G FOR QINSHAN | RTD |  | J# 72602- 72604 | 7/25/25 | 7/25/25 | Oct-28-25 | ✓ |  | Feb 13, 26 Jan 20, 26 Jan 9, 26 | Feb 20, 26 Jan 27, 26 Jan 16, 26 | Mar 6, 26 Feb 3, 26 Jan 30, 26 | Oct-29-25- The shipment date has been changed due to a backlog in the QC department. -detail parts in inspection, assembly Nov-26-25- The shipping date needs to be changed-need to do phosphate, dynaloy (98-31952-88-1-DD-C, 98-31952-89-1-DD-C) Dec-11-25- Still confirming the realistic date for the shipdate Jan-6-26- Need to change the date due to the Dynaloy process for “98-31952-87-1-DD-D,” “98-31952-88-1-DD-D,” and “98-31952-89-1-DD-D” was delayed, additional manufacturing work is still required. Jan-14-26- Need to change the date due to mistakes in the Dynaloy and Phosphate processes, the parts need to be sent back to the subcontract company. |  | 70% | 10% |  | Laila Parveen | Milestone: ( KICK OFF MEETING- SEPT-4-25) 1) 30% upon submission of Unpriced PO Inv# 2) 70% delivery of all item and Docs Inv#
RT98-87920-PN-R014 | GROUP 5 FOR QINSHAN | RTD |  | J# 72651-72654 | Aug-16-25 | Aug-14-25 | Feb-16-26 | ✓ |  | Apr 2, 26 Jan 26, 26 | Apr 9, 26 Feb 2, 26 | Apr 23, 26 Feb 16, 26 | Delivery date accepted from Jan-22-25- to Feb-16-25 due to workload Nov-12-25- on trak- no issues at this time Nov-26-25- RT-87920-74245-000-1-GA-E (J#72652) : DDR approved, manufacturing still on track Dec-11-25- Confirming the manufacturing status Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- The shipment date will be changed to align with the schedule for the integrating test. |  | 45% | 5% |  | Amritha Gopan | Milestones: 1) 30% Upon submittal of unpriced PO 2) 30% Upon Comp. 50% of Projecct 3) 40% upon Delivery & Docs
RT98-87710-PN-R006 | END SHIELD MEASUREMENT TOOL FOR QINSHAN | RTD | 0 | J# 72621 | aug-1-25 | Aug-1-25 | Nov-14-25 | N/A |  | Dec 22, 25 Jan 5, 26 | Dec 24, 25 Jan 15, 26 | Jan 23, 26 Jan 14, 26 | Oct-29-25- Under calibration, scheduled to be returned on Nov 7. Nov-5-25- 8 gauges return to factory for replacement Nov-12-25- Still waiting for indicator Nov-26-25- Still waiting for indicator (delivery will be tentaively 6 weeks) Dec-11-25- Stll waiting indicator Dec-17-25- Stll waiting indicator info Jan-6-26- Manufacturing completed(Dec 22), submitted Docs(Dec 24)-waiting approval Jan-14-26- Still waiting approval for QA reports |  | 95% | 10% | On Schedule | Laila Parveen | NO MILESTONES
RT98-87272-PN-R020- Rev.1 | MOCKUP COLUMN FOR COMMISION OF TILTER | RTD |  | J# 72624 | 2008-05-25 | 2008-05-25 | Jan-26-26 | ✓ |  | Jan 30, 26 Jan 5, 26 | Feb 6, 26 Jan 12, 26 | Feb 20, 26 Jan 26, 26 | Oct-22-25- Welding will be done in the next week Nov-5-25- on track, no issues at this time Nov-11-25- on track, no issues at this time Nov-26-25- The shipping date needs to be changed-Because of big machine capacity issue. Dec-11-25- Still on track Dec-17-25- Still on track-no issues at this time Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 70% | 10% | On Schedule | Etianne Machado | MILESTONES: 1) 30% Upon Submission of unpriced PO Inv# 2) 30% Upon Approximately 50% completion Inv# 3) 40% Upon delivery of all items & Doc Inv#
RT98-87250-PN-R007 | INSTALLATION WORKTABLE AND INSTALLATION WORKTABLE SUPPORT FRAME | RTD | 0 | J# 72438-72441 | June-2-25 | June-3-25 | Oct-16-26 | N/A |  | 1set : Apr 30, 26 Feb 6, 26 2set : Sep 25, 26 | 1set : May 7, 26 Feb 13, 26 2set : Oct 2, 26 | 1set : May 21, 26 Feb 27, 26 2set : Oct 16, 26 | Oct-10-25- New Updated Software schedule needs to be submitted to capture 2- different delivery dates Oct-29-25- No issue at this moment Nov-5-25- No issue at this moment Nov-11-25- Still on track, no issues at this time. Nov-26-25- We cannot met the 1set Feb- we have material hardware issue Dec-11-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26 Confirmed the realistic date for 1set shipping date |  | 15% | 5% | On Schedule | Laila Parveen | Milestone: 1) 30% upon submittal of Unpriced PO 06/27/25 INV# 2) 30% Upon 50% compltetion of PO 12/12/25 INV# 3) 20% When ready for Function Test 08/28/26 INV# 4) 10% After del'v of 1 Worktable & Supt frame 02/816/26 INV# 5) 10% After delivery of remain'g Items 10/16/26 INV#
RT98-88230-PN-R010 | FEEDER TEMPLATES | RTD | 0 | J# J# 72234-72242 | 2025-03-20 | 2025-03-20 | 2025-10-17 | N/A |  | Mar 13, 26 Feb 13, 26 | Mar 20, 26 Feb 20, 26 | Apr 3, 26 Mar 6, 26 | Oct-22-25- Machining is still in progress Oct-29-25- The shipment date has been changed due to a factory's floor capacity issue. Machining done-welding, inspection, assembly Nov-12-25- Shipdate need to be revised-To prioritize the processing of RT79 parts Nov-26-25- The shipping date needs to be changed-rechecked the realistic date in order to prioritize the RT79 parts. Dec-17-25- Still on track Jan-7-26- Fit test info-still waiting from Candu, Need to change the date due to Inspection backlog Jan-14-26- Still working on manufacturing |  | 70% | 60% | On Schedule | Laila Parveen | Milestone: 1) 30% upon submittal of Unpriced PO Inv# 52700 2) 15% upon 40% average compltn of MFG Inv# 52864 3) 15% upon 75% average completion of MFG Inv# 4) 40% Upon Delivery of items and Docs Inv#
RT98-87000-PN-R012 | PITCH-YAW MOUNTING TABLE AND PITCH YAW MOUNTING FRAME TOOL | RTD | 0 | J# 72367-72368 | May-5-25 | May-5-25 | Jul-29-26 | ✓ |  | 1set : Mar 19, 26 Feb 13, 26 Feb 6, 26 2set : Jul 8, 26 | 1set : Mar 26, 26 Feb 20, 26 Feb 13, 26 2set : Jul 15, 26 | 1set : Apr 9, 26 Mar 6, 26 Feb 27, 26 2set : Jul 29, 26 | Oct-6-25- Delivery date for 1set will be Feb 27,26- for integration testing Nov-5-25- Stil on track- no issues at this time Nov-12-25- Still on track, no issues at this time. Nov-26-25- The date has been changed after reviewing a more realistic schedule. Dec-17-25- Still on track Jan-7-26- Still working on manufacturing for 1set Jan-14-26 Confirmed the realistic date for 1set shipping date |  | 1 set : 40% 2 set : 10% | 10% | On Schedule | Laila Parveen | MileStone: 1) 30% Upon submission of Unpriced PO's 05/30/25 Inv# 52946 2) 25% Upon completion of 50% of Project 08/29/25 Inv# 3) 20% Upon Completion of 80% of Project 02/13/26 Inv# 4) 25% Upon Delivery 07/29/25 Inv#
RT98-88010-PN-R010 | GROUP 7A OF TOOLS FOR QINSHAN | RTD |  | J# 72713-72726 | 2025-07-24 | 2025-07-24 | 2026-03-16 | ✓ |  | 2026-02-23 | 2026-03-02 | 2026-03-16 | Noissue at this time Jan-7-26- Manufacturing is still in progress Jan-14-26- Requesting the meeting for Technical Summary of Exceptions (email Jan-13 4:58 PM)-need to confirm the realistic shipping date |  | 5% |  |  | Laila Parveen | Milestones: 30%- Unpriced PO: 30%- Completion fo r50% of Project 40%- Upon completion- Delivery:
RT98-87920-PN-R017 | GROUP 7C ( LIFTING BEAMS ) FOR QINSHAN | RTD |  | J#72840-72844 | 2025-10-03 | 2025-10-03 | 2026-02-13 | ✓ |  | Mar 13, 26 Feb 27, 26 Jan 23, 26 | Mar 20, 26 Mar 6, 26 Jan 30, 26 | Apr 9, 26 Mar 20, 26 Feb 13, 26 | Oct-6-25- All Procedures Submitted Noissue at this time Nov-26-25- The shipping date needs to be changed-Because the material has not been ordered yet. Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Confirmed the realistic date for shipping |  | 20% |  |  | Laila Parveen
RT98-87640-PN-R005 | GROUP 7D (CARTS & RACK) FOR QINSHAN | RTD |  | J#72818-72820 J# 72967 | 2025-09-29 | 2025-09-29 | 2026-01-30 | ✓ |  | Feb 27, 26 Feb 6, 26 - Apr 1, 26 | Mar 6, 26 Feb 13, 26 - Apr 8, 26 | Mar 20, 26 Feb 27, 26 - Apr 22, 26 | Delivery date adjust from Jan-30-26- to Feb-27-26 due to workload Oct-7-25- All procedures submitted Oct-15-25- Kick-off meeting Noissue at this time Nov-26-25- The shipping date needs to be changed-Because of large mill machine capacity issue. Dec-11-25- add the parts for 1pc "EF tool rack"-shipdate will be Apr-22,26 Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 15% |  |  | Laila Parveen | Milestones: 30% Submission of Unpriced PO: 30% - Completion of Long lead Items 40% Upon completeion & Delivury
RT98-87920-PN-R015 | GROUP 5F FOR QINSHAN | RTD |  | J#72811-72817 | 2025-09-29 | 2025-09-29 | 2026-02-05 | ✓ |  | Mar 6, 26 Feb 5, 26 | Mar 13, 26 Feb 12, 26 | Mar 27, 26 Feb 23, 26 | Delivery date adjust from Feb-5-26- to Feb-23-26 due to workload Oct-6-25- All procedures submitted Noissue at this time Nov-26-25- The shipping date needs to be changed-Because the material is currently being ordered. Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 10% |  |  | Laila Parveen | Milestone: 30% Upon Submission of Unpriced PO: 30% Completion of Long Lead Time 40% Upon Completion and Delivery:
RT98-87590-PN-R006- Rev.1 | EFSF REMOVAL TOOL +Electrical | RTD | 0 | J# 72373 | May-5-25 | May-5-25 | Oct-9-26 | ✓ |  | 1set : May 26, 26 Mar 13, 26 Feb 2, 26 2set : Sep 18, 26 | 1set : Jun 2 ,26 Mar 20, 26 Feb 9, 26 2 set : Sep 25, 26 | 1set : Jun 16, 26 Apr 3, 26 Feb 23, 26 2set : Oct 9, 26 | Oct-6-25- Delivery date for 1set will be Feb 23,26 for integration testing Nov-13-25-LCP dwg waiting Nov-26-25- The shipping date needs to be changed-Because of the big machine capacity issue. Still waiting LCP dwg-sent remind email (Nov-21) Dec-11-25- Confirming the manufacturing status, ship date Dec-17-25- We can't meet the date for 1set in Feb-22-26-Current manufacturing progress at the plant as well as the electrical issue that was shared during meeting in Dec-17. Jan-7-26- Still working on manufacturing Jan-14-26- Confirmed the realistic shipping date |  | 35% | 10% | On Schedule | Amritha Gopan | Milestone: 1) 30% Upon submission of Unpriced PO's 05/30/25 Inv# 2) 10% AT 50% of Project 10/01/25 Inv# 3) 10% when ready for Unit 1 Function Test 02/06/26 Inv# 4) 10% Upon Delivery of Unit 1 03/16/26 Inv# 5) 25% After Delivery of All items and Accpt Doc 10/9/26 Inv# 6) 15% At 50% completion of Remaiing Qty 08/03/26 Inv#
RT98-87590-PN-R007 | MOCKUP LWTF TROLLEY FOR QINSHAN | RTD | 0 | J# 72280 J# 72948 | 2025-04-01 | 2025-04-01 | 2025-08-15 | N/A |  | Mar 16, 26 Jan 16, 26 | Mar 23, 26 Jan 23, 26 | Apr 6, 26 Feb 6, 26 | Oct-21-25- All documents were submitted -waiting Approval-changed the delivery date Oct-28-25- Meeting held regarding frame parts. Currently confirming cost and schedule. Nov-6-25- Frame parts quote will be submitted. Nov-12-25- got clarification info-need to review the info and submit Quote (Nov-14) Nov-26-25- RT-87640-70300-000-1-GA-E (J#72280) : Manufacturing completed RT-87640-70300-000-1-GA-E (J#72948) : Ordering material Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 50% | 85% |  | Laila Parveen | Milestones: 1) 0%- Upon Submission of Unpriced PO: May-9-25 Inv#. 52759 2) 70%- Upon Delivery of Equipment % Doc: Aug-15-25 Inv#
RT98-87920-PN-R013 | GROUP 5B FOR QINSHAN | RTD |  | J# 72625 ~ 72635 | Aug-8-25 | Aug-8-25 | May-28-26 | ✓ |  | 2026-05-07 | 2026-05-14 | 2026-05-28 | 4) Tool ID for QINSHAN starts at "200" 5) Requested for 3D models in STEP FORMAT Oct-29-25- Noissue at this time Nov-5-25- on trak- no issues at this time Nov-12-25- on trak- no issues at this time Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 10% | 5% |  | amritha Gopan | NO Milestone
RT98-88040-PN-R004 | GROUP 5D FOR QINSHAN | RTD |  | J# 72775-72780 | NEW |  | 1line-5line : Jul 17,26 6 line : Aug 28, 26 | ✓ |  | 1line-5line : Jul 6, 26 Jun 26,26 6 line : Aug 7, 26 | 1line-5line : Jul 13, 26 Jul 3,26 6 line : Aug 14, 26 | 1line-5line : Jul 27, 26 Jul 17,26 6 line : Aug 28, 26 | Oct-3-23- All procedures Submitted Nov-5-25- on track, no issues rt this time Nov-11-25- on track, no issues at this time Nov-26-25- on track Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Confirmed the realistic shipping date |  | 20% | 5% | On Schedule | Etianne Machado | MILESTONES: 1) 30% Upon Submission of unpriced PO Inv# 2) 30% Upon Approximately 50% completion Inv# 3) 40% Upon delivery of all items & Doc Inv#
RT98-87000-PN-R018 | BRT BELLOWS REMOVAL CUTTING TOOL FOR QINSHAN | RTD |  | J# 72924-72940 | NEW |  |  |  |  | Jul-20-26 | Jul-27-26 | Aug-10-26 | Dec-2-25- Kick off meeting @10am Dec-17-25- Still on track Jan-7-26- Still working on manufacturing Jan-14-26- Still working on manufacturing |  | 5% |  |  | Laila Parveen
RT98-87640-PN-R004 | LWFT & AIRLOCK TROLLEY & TRACK ASSY | RTD |  | J# 72728-72736 | 2025-09-09 | 2027-04-15 | 2027-05-27 | ✓ |  | 2027-02-03 | 2027-02-17 | 2027-02-24 | Oct-29-25- No issue at this moment Nov-5-25- on track, no issues at this time Nov-7-25-DDR9001 submitted Nov-12-25- on track, no issues at this time Nov-26-25- on track Dec-11-25- continually test procedures and planting test procedures are not accept-waiting electrical engineer Dec-17-25- Still pending for electrical issues. Jan-7-26- Need to update the SOE Jan-14-26- Still working on manufacturing |  | 15% | 5% | On Schedule | Etianne Machado | MILESTONES: 1) 30% Upon Submission of unpriced PO Inv# 2) 30% Upon Approximately 50% completion Inv# 3) 15% Prior to sucessful FAT Inv# 4) 25% upon completion of shipment Inv#
RT98-87000-PN-R023 | ROLLED JOINT SENTRING | RTD |  | J# 72959 | NEW |  |  |  |  | Jan 5, 26 Dec 23, 25 | Jan 7, 26 Dec 30, 25 | Jan 23, 26 Jan 15, 26 | Dec-11-25- Still on track Dec-17-25- Still on track Jan-7-26- Manufacturing completed (Jan-5),submitted QA Docs (Jan-7)-waiting for approval Jan-14-26- Waiting approval for QA reports |  | 95% |  |  | Etianne Machado
RT79-87540-PN-R004 | STUD INSTRATION TOOL | RTD |  | J# 72966 | [5 empty] | Feb 13, 26 Jan 19, 26 | Feb 20, 26 Jan 26, 26 | Mar 6, 26 Feb 9, 26 | Dec-11-25- Still on track Jan-7-26- Waiting for Candu answer about DDR Need to confirm the each date Jan-14-26- Need to change the each date due to the welding backlog |  | 20% | 5% | On Schedule | Wendy Wu
RT98-87000-PN-R021 | FEEDER COUPLING ASSY FOR QINSHAN | RTD |  | J#73001-73004 | DEC-23-25 |  |  |  |  | Feb-3-26 | feb-17-26 | feb-24-26 | New order Dec-31-25- All Procedures Submitted Jan-9-26- RT-87120-70184-002-1-DD-B- 24 gauge CRS1018 not commercially stocked advise if 1008 is acceptable ( pending) Jan-14-26- we are confirming delivery date by next conference call |  | 5% |  |  | Wendy Wu | NO MILESTONE: DELIVERY OF ALL ITEM + DOCUMENTS
RT79-88010-PN-R003- R.2 | GROUP 8 TOOLS FOR C1R | RTD |  | J# 73007-73008 | DEC-24-25 |  |  |  |  | JAN-30-26 | FEB-13-26 | FEB-20-26 | New order Jan-14-26- we are confirming delivery date by next conference call |  | 5% |  |  | Laila Parveen | MILESTONE: 1) 25% upon submission for procedures 2) 25% Upon receipt of Major Materials 3) 25% Upon start of assy 4) 25% Upon delivery of Equipment & Docs
RT98-87540-PN-R002- Rev.1 | GROUP 15 TOOLS FOR QINSHAN | RTD |  | J# 73009 | DEC-24-25 |  |  |  |  | JAN-30-26 | FEB-13-26 | FEB-20-26 | New order Jan-14-26- we are confirming delivery date by next conference call |  | 5% |  |  | Laila Parveen | NO MILESTONES- CHANGE ORDER # 1
RT79-31912-PN-R006 | GARTER SPRING FLASK & TROLLEY | RTD |  | J# 73027 | DEC-30-25 |  |  |  |  | APRIL-1-26 | APRIL-15-26 | APRIL-22-26 | New order Jan-14-26- we are confirming delivery date by next conference call |  | 5% |  |  | Etianne Machado | MILESTONE: 1) 30% UPON SUBMITTAL OF UNPRICED PO 2) 70% UPON DELIVERY OF ALL ITEMS INCLUDING DOCUMENTS
RT98-87540-PN-R003 | PA STUD INSTALLATION TOOL & SPRING PIN INSTALLATION TOOL-HARDWARE TOOL QINSHAN | RTD |  | J# 73038-73040 | JAN-7-26 |  |  |  |  | MAR-9-26 | MAR-23-26 | Mar-30-26 | New Order Jan-9-26- Welding / Painiting / Dim& Visual procedures submitted ( Pending) Jan-14-26- we are confirming delivery date by next conference call |  | 5% |  |  | Raza Talpur | NO MILESTONE- DELIVERY COMPLETE WITH QA DOC'S